## Sheet1
Project Name: Cyberbullying Detection Using Support Vector Machine (SVM) Algorithm
| Project Lead: |  |  | Samantha Mallari
| Project Start Date: |  |  | 2017-02-27 | time axis 2017-02-27 to 2017-04-24
| Display Week: |  |  | 1 |  |  |  |  | 2017-02-27: Week 1; 2017-03-06: Week 2; 2017-03-13: Week 3; 2017-03-20: Week 4; 2017-03-27: Week 5; 2017-04-03: Week 6; 2017-04-10: Week 7; 2017-04-17: Week 8
[9 empty] | 2017-02-27 | [6 empty] | 2017-03-06 | [6 empty] | 2017-03-13 | [6 empty] | 2017-03-20 | [6 empty] | 2017-03-27 | [6 empty] | 2017-04-03 | [6 empty] | 2017-04-10 | [6 empty] | 2017-04-17
WBS | Task | Lead | Prede cessor | Start | End | Cal. Days | % Done | Work Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | Planning
1.1 | Kick-off Meetings
1.1.1 | Client Meetings
1.1.1.1 | First Meeting
1.1.1.2 | Second Meeting
1.1.2 | Consultant Meetings
1.1.2.1 | First Meeting
1.1.2.2 | Second Meeting
1.1.2.3 | Third Meeting
2 | Research
2.1 | Text Classification Concepts
2.2 | Additional Text Pre-processing Techniques
2.3 | Message-passing Protocol Mechanism
2.4 | ISO-9126 Software Development Standard
2.5 | Internet Privacy Terms
2.6 | Additional Related Literatures
2.7 | Surveys
2.7.1 | Cyberbullying Survey for APC Students
2.8 | Existing Cyberbullying Data in APC
3 | Experimentation
3.1 | Data Collection
3.2 | Dataset Cleaning
3.3 | Tokenization
3.4 | Data Annotation
3.5 | Bag-of-Words
3.6 | Support Vector Machine (SVM) Algorithm Implementation
4 | Software Development
4.1 | Front-end Development
4.1.1 | Graphical User Interface
4.1.1.1 | User
4.1.1.1.1 | Homepage | Faih
4.1.1.1.2 | Timeline | Faih
4.1.1.1.2.1 | Input Post | Paulo
4.1.1.1.2.2 | Output Post | Paulo
4.1.1.1.3 | Profile | Faith
4.1.1.1.4 | Settings | Faith
4.1.1.2 | Admin
4.1.1.2.1 | Log-in | Faith
4.1.1.2.2 | Reports Page
4.1.1.2.2.1 | Output user report | Paulo
4.1.1.2.2.2 | Email Notifications | Paulo
4.2 | Back-end Development
4.2.1 | Website Add-in
4.2.1.1 | Automated Statement Acquisition | Sam & Eva |  | 2017-02-27 | 2017-03-03
4.2.1.2 | Automated Tokenization | Sam & Eva |  | 2017-02-27 | 2017-03-03
4.2.1.3 | Automated Statement Cleaning | Sam & Eva |  | 2017-02-27 | 2017-03-06
4.2.1.4 | Automated Bag-of-Words | Sam & Eva |  | 2017-02-27 | 2017-03-06
4.2.1.5 | Automated SVM Implementation | Sam & Eva |  | 2017-03-06 | 2017-03-13
4.2.1.6 | Automated Re-learning
4.2.2 | Message-passing Protocol
4.2.3 | Database
4.2.3.1 | Set-up / Configuration | Paulo
4.2.3.2 | CRUD Functionality | Paulo
5 | Documentation
5.1 | Vision and Scope document | Jason
5.2 | Project plan
5.2.1 | Project Overview | Sam & Faith
5.2.2 | Project Organization | Sam & Faith
5.2.3 | Managerial Plans
5.2.3.1 | Start-up Plan
5.2.3.1.1 | Estimates
5.2.3.1.2 | Staffing
5.2.3.1.3 | Resource Acquisition
5.2.3.1.4 | Project Staff Training
5.2.3.2 | Work Plan
5.2.3.2.1 | Work Breakdown Structure | Sam & Eva
5.2.3.2.1.1 | Gantt Chart | Sam
5.2.3.2.2 | Schedule Allocation
5.2.3.2.3 | Resource Allocation
5.2.3.2.4 | Budget Allocation
5.2.3.3 | Project Tracking Plan
5.2.3.3.1 | Requirements Management
5.2.3.3.2 | Schedule Control
5.2.3.3.3 | Budget Control
5.2.3.3.4 | Quality Control
5.2.3.3.5 | Reporting
5.2.3.3.5.1 | Project Status Reports
5.2.3.3.6 | Project Metrics
5.2.3.4 | Risk Management Plan
5.2.3.5 | Project Closeout Plan
5.2.4 | Technical Process Plans
5.2.4.1 | Process Model
5.2.4.2 | Methods, Tools, and Techniques
5.2.4.3 | Infrastructure
5.2.4.4 | Product Acceptance
5.2.5 | Supporting Process Plans
5.2.5.1 | Configuration Management
5.2.5.2 | Verification and Validation
5.2.5.3 | Documentation
5.2.5.4 | Quality Assurance
5.2.5.5 | Reviews and Audits
5.2.5.6 | Problem Resolution
5.2.5.7 | Subcontractor Management
5.2.5.8 | Process Improvement
5.2.6 | Additional Plans
5.2.7 | Appendices
5.3 | Wiki Documentation
5.3.1 | Introduction | Sam
5.3.2 | Review of Related Literature | Faith
5.3.3 | Theoretical Background | Faith
5.3.4 | Proposed Solution to the Problem | Eva & Paulo |  | 2017-02-27 | 2017-03-03
5.3.4.1 | System Diagrams
5.3.4.1.1 | System Architecture Diagram | Eva |  | 2017-02-27 | 2017-03-03
5.3.4.1.1.1 | Entity Relationship Diagram | Sam |  | 2017-02-27 | 2017-03-05
5.3.4.1.2 | Context Flow Diagram | Eva |  | 2017-02-27 | 2017-03-03
5.3.4.1.3 | Data Flow Diagram | Eva |  | 2017-02-27 | 2017-03-03
5.3.4.1.4 | UML Diagrams | Eva |  | 2017-02-27 | 2017-03-03
5.3.4.2 | Screen Designs
5.3.5 | Results and Discussions
5.3.6 | Conclusions and Recommendations
5.3.7 | Appendices
5.4 | Software Requirements Specification document | Sam & Jason |  | 2017-02-27 | 2017-03-03
5.5 | Test Plan | Eva & Jason |  | 2017-02-27 | 2017-03-06
5.5.1 | Introduction | Eva & Jason |  | 2017-02-27 | 2017-03-06
5.5.2 | Test Areas and Specifications | Eva & Jason |  | 2017-02-27 | 2017-03-06
5.5.2.1 | Use Case Diagrams / Specifications | Eva & Jason |  | 2017-02-27 | 2017-03-06
5.5.2.2 | Process Event Table | Eva & Jason |  | 2017-02-27 | 2017-03-06
5.5.3 | Test Cycle Transitions | Eva & Jason |  | 2017-02-27 | 2017-03-06
5.5.4 | Milestone | Eva & Jason |  | 2017-02-27 | 2017-03-06
5.5.5 | Test Deliverables and Execution | Eva & Jason |  | 2017-02-27 | 2017-03-06
5.5.6 | Environmental Needs | Eva & Jason |  | 2017-02-27 | 2017-03-06
5.5.7 | Planning Risks and Contingencies | Eva & Jason |  | 2017-02-27 | 2017-03-06
5.5.8 | Approvals | Eva & Jason |  | 2017-02-27 | 2017-03-06
5.6 | Test Cases | Eva & Jason |  | 2017-02-27 | 2017-03-06
5.7 | Project Status Reports
5.7.1 | Week 3 | Sam |  | 2017-02-27 | 2017-03-03
5.7.2 | Week 4 | Sam |  | 2017-02-27 | 2017-03-03
5.7.3 | Week 5 | Sam |  | 2017-02-27 | 2017-03-03
5.7.4 | Week 6 | Sam |  | 2017-02-27 | 2017-03-03
5.7.5 | Week 7 | Sam |  | 2017-02-27 | 2017-03-03
5.7.6 | Week 8 | Sam
5.7.7 | Week 9 | Sam
5.7.8 | Week 10 | Sam
5.8 | User and Admin Manuals
6 | Closeout
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … The WBS uses a formula to control the numbering, but the formulas are different for different levels.
Note on B7: Task Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version includes template rows that allow you to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.